## Overall Open Actions
Schools Forum |  |  |  |  | Last updated:
Action No. | Date | Agenda item | Back ground | Decision / Action Made | Owner | Due date | Latest update | Previous updates (and dates)
7 |  |  | There has been a challenge on the equalities agenda and how well our schools have improved in the recent years. The education outcomes are good overall but the gap between the disadvantaged and the rest is getting bigger. Other LAs have more school funding to support disadvantaged pupils than our schools do. | HS to do a piece of work with schools on how we can try and unpick this gap and how this compares with other LAs and the benefits they have especially with children of a disadvantage. | HS | On-going
9 | 2023-11-02 | Schools in Financial Difficulty update | To provide an update on Schools in Financial Difficulty | MS to carry out a piece of work to collect data from Academies as report only based on Maintained Schools - to contact CEO's from schools to participate in collection of data. | MS | 2023-12-31
12 | 2023-12-07 | Schools Funding Campaign Update | After the last meeting a group of us met with Cllr Ian Boulton and Daniel Ward (Comms) and we gave a representation of the impact we are seeing in schools on how we are trying to make our budgets balance and both Ian and Daniel were shocked to hear that in some schools the heating needed to be turned down, staff not being replaced and reducing support for families and lobbying the change around the fairer funded guarantee. | Pippa and Mustafa to meet before Christmas to get the letter to the DfE between now and January. | PO / MS | On-going
13 | 2023-12-07 | Comms Plan | Comms. A letter to go out to schools next week advising key messages that we have to top slice. This requires Secretary of State approval and supports the SEND Strategy. | Hilary to draft the letter and send to Pippa and Susie Weaver as Chair of the HNWG. | HS | 2024-01-01
14
15

## Closed Actions
Action No. | Date | Agenda item | Back ground | Decision / Action Made | Owner | Due date | Latest update | Previous updates (and dates)
1 | 2023-09-28 | Item 7 - Dedicated Schools Grant 2022/23 Outturn | To invite members to the Education / Skills / Employment / Business – Cabinet Members Briefing on 19th October at 9am | SF members available to join the meeting on 19th October are Pippa Osborne, Dave Baker, Louise Leader, Ross Newman and Diane Owen. | MT/CC | 2023-11-02 | Complete
2 | 2023-09-28 | Item 9 Current Position on school places across schools system in South Gloucestershire | This paper sets out the current position on our sufficient places in the primary and secondary sector phase and any actions to address any issues. We do currently have sufficient primary places but we do need to monitor the secondary phase closely | Hilary to take away and look at the data, especially around Bradley Stoke and Kings Oak as they are all through schools. | HS | 2023-11-02 | Hilary confirmed 10-10-23 - it doesn’t need to go back to the Forum before the update next year, for Hilary to note that we needed to show these two schools as all age
3 |  | Item 10 Safey Valve Update | We had been asked to meet DfE officials regarding our Safety Valve plan and they had raised prior to the meeting the fact that we seem to be slipping against the target and challenge. We presented some of the progress that we had all been making together with the investment in cluster funds and the number of EHCPs where for the first time in the data we were below the England average. We did also make a case for extra funding against inflation and we also made a bid or asked for more capital funding and invest in more SEND places and an extension in our recovery plan. | Is there some scope for a joint letter from Mustafa, Hilary or Ian Boulton to work with the Council to lobby on our behalf and may be include those who represent the sectors currently and then approach their sectors rep. | MS | TBC | Linked to action 1 - close
4 | 2023-09-28 | Item 11 Banding and Top-Up Funding arrangements for Pupils in Education and Healthcare Plans (EHCPs) - Year 2 | We introduced a new top up and banding arrangement just over a year ago. We agreed new top up rates and banding process and agreed a 3-year transition period rate for Yr1. Yr2 starts this September and we said we would give an update to the Forum and assess our ability to move to the next phase of our transition. | Mustafa to invite a small group of school reps to next year’s costing exercise (and to share a copy of the LA model to any schools interested) | MS | July - August 2024 | Close
5 | 2023-09-28 | Item 12 Schools Forum Forward Plan | Annual Planner | Remove membership update from Forward plan for November. Defer - Proposed Financial Amendments Breach Funding to December | MT MT | 2023-11-02 | Complete
6 | 2023-11-02 | Other items the chair decides are urgent | Meeting held with LA, Cabinet Member, Pippa, Dave, Louise, Diane on 19th October - Shared extensive list of sacrifices schools have to make to balance school budgets, also mentioned increase in EAL children but lack of funding means we don’t have resources in terms of staff to support them as we would like to | Pippa to type up notes of meeting & list of sacrifices made by relevant schools and circulate to the Forum | PO | Complete
8 | 2023-11-02 | Setting the Schools Budget 2024-2025 and Consultation on £2.2m DSG Block Transfer | Discussion held on Proposed options to agree or decline the £2.2m DSG Bock Transfer | a) CC to note in the minutes b) PO to draft agreement on behalf of members of the forum for option 1 with some stipulations to be included, to add text in chat re paper from David Jenkins - send to MS to forward to Members & Secretary of State c) CC to add Option 2 into the minutes as not stated in the report. | CC - Complete PO / MS CC - Complete | Complete
10 | 2023-11-02 | Q1 Financial Performance update | Issue of SEND pupils in mainstream with expensive packages because of a lack of specialist places should be reviewed. | CC to add to HNWG agenda re; number of students with EHCP's in mainstream | CC | Complete
11 | 2023-11-02 | Forward Plan | Normally the EYSFF settlement from the Government comes very late in December leaving little time to consult. The DFE have said this will be available in November this time so could it be consulted on and brough to the Forum earlier than normal. | HS to take this forward as an action with Jo Briscombe who might bring a report to Schools Forum at the end of December/early January. | JB/HS | Complete - on agenda 18-01-24

## Attendance 2023
Membership |  | Attendance 2023
Name | Service | 2023-09-28 | 2023-11-02 | 2023-12-07
Aaron Jefferies | Primary Governor, Coniston Primary School | Y | Y | A
Andy Watson | LEAF Trust Representative
Bernice Webber | Headteacher, Old Sodbury CE Primary School | Y
Caroline Churchill | Note Taker SGC | Y | Y
Caroline Warren | Finance Business Partner SGC | Y | Y
Chris Sivers | Executive Director People's Department SGC | A | A | A
Clare Haughton | Page Park Pre-School
Dave Baker | Vice Chair - CEO, Olympus Academy Trust | Y | Y | A
David Jenkins | Governor, Crossways Schools | Y | A
David Williams | Diocese of Gloucester | Y | A | A
Deb Luter | Schools Finance Team Leader SGC | Y | Y
Debbie Beazer | LEAF Trust Representative | Y
Diane Owen | Chair to Academy Council at King’s Oak Academy | Y | Y | Y
Hilary Smith | Service Director Education, Learning and Skills SGC | Y | Y
Ian Boulton | Cabinet Member - Schools, Skills, Employment and Business | Y | A | A
Julia Anwar | Head of Business Operations, Olympus Academy Trust | Y | Y | Y
Katherine Absalom | Primary Headteacher Park and Parkwall Primary Federation | A
Katherine Marks | Headteacher, Frenchay Primary | A
Kim Garland | Headteacher, Brimsham Green School | A | Y
Lisa Parker | Headteacher Warmley Park School | A | Y
Louise Leader | Headteacher, Pathways Learning Centre | Y | Y
Malcolm Strange | Diocese of Bristol | A | Y | A
Michelle Trigg | Clerk to the Schools Forum SGC | Y | Y | A
Mustafa Salih | Service Director Resources and Business SGC | Y | Y | Y
Nicky Edwards | Early Years Schools Forum Representative |  | Y | Y
Nicola Bailey | Headteacher, Meadowbrook Primary School | A | Y
Nicola Jones | Trustee for Enable Trust. | R - Tamsin Moreton | Y + Tamsin
Pippa Osborne | Chair - Headteacher Christ Church Junior School | Y | Y | Y
Ross Newman | Early Years Schools Forum Representative | Y | Y | A
Stuart Evans | South Gloucestershire and Stroud College | Y
Sue Wright | Finance Director CSET |  | Y
Susie Weaver | Executive Principal, Cabot Learning Federation | Y | Y | Y
Will Roberts | CEO CSET |  | Y | Y

## Action Summaries
Action No. | Date | Agenda item | Back ground | Decision / Action Made | Owner | Due date | Latest update | Previous updates (and dates)
1 | 2023-09-28 | Item 7 - Dedicated Schools Grant 2022/23 Outturn | To invite members to the Education / Skills / Employment / Business – Cabinet Members Briefing on 19th October at 9am | SF members available to join the meeting on 19th October are Pippa Osborne, Dave Baker, Louise Leader, Ross Newman and Diane Owen. | MT/CC | 2023-11-02 | Complete
2 | 2023-09-28 | Item 9 Current Position on school places across schools system in South Gloucestershire | This paper sets out the current position on our sufficient places in the primary and secondary sector phase and any actions to address any issues. We do currently have sufficient primary places but we do need to monitor the secondary phase closely | Hilary to take away and look at the data, especially around Bradley Stoke and Kings Oak as they are all through schools. | HS | 2023-11-02 | Hilary confirmed 10-10-23 - it doesn’t need to go back to the Forum before the update next year, for Hilary to note that we needed to show these two schools as all age
3 |  | Item 10 Safey Valve Update | We had been asked to meet DfE officials regarding our Safety Valve plan and they had raised prior to the meeting the fact that we seem to be slipping against the target and challenge. We presented some of the progress that we had all been making together with the investment in cluster funds and the number of EHCPs where for the first time in the data we were below the England average. We did also make a case for extra funding against inflation and we also made a bid or asked for more capital funding and invest in more SEND places and an extension in our recovery plan. | Is there some scope for a joint letter from Mustafa, Hilary or Ian Boulton to work with the Council to lobby on our behalf and may be include those who represent the sectors currently and then approach their sectors rep. | MS | TBC | Linked to action 1 - close
4 | 2023-09-28 | Item 11 Banding and Top-Up Funding arrangements for Pupils in Education and Healthcare Plans (EHCPs) - Year 2 | We introduced a new top up and banding arrangement just over a year ago. We agreed new top up rates and banding process and agreed a 3-year transition period rate for Yr1. Yr2 starts this September and we said we would give an update to the Forum and assess our ability to move to the next phase of our transition. | Mustafa to invite a small group of school reps to next year’s costing exercise (and to share a copy of the LA model to any schools interested) | MS | July - August 2024 | Close
5 | 2023-09-28 | Item 12 Schools Forum Forward Plan | Annual Planner | Remove membership update from Forward plan for November. Defer - Proposed Financial Amendments Breach Funding to December | MT MT | 2023-11-02 | Complete

## Overall Closed Actions (hidden)
ICS SLT - Overall Closed Actions
Action No. | Date | Status | Agenda item | Action | Owner | Due date | Latest update (and date) | Previous updates (and dates)
Gov 140 | 2017-03-09 | closed (21/2) | Audit activity | Ensure collation of themes arising from the audits is completed to identify and put steps in place to address development areas within the overall service or with specific teams | CB | 2017-03-31 | 2/2 - CB: the tracker has been used on a smaller basis during January with full roll out in February. Themes summarised within this | 28/4 - A draft tracker is being formulated which records the outcome of audits and agreed actions. These actions will then be monitored by PSW/CSW to ensure they are completed. Recommend that a report on progress of the tracker is reported to SLT/Governance on an agreed periodic basis 24/5 - In place; however a more robust tracker system is being planned for development in July 2017 26/7: Meeting 31/8 to look to progress this 1/11 - Aimee Williams CSW is leading on this work which continues to be work in progress. 7/12 - Draft tracker being considered at SMs meeting on Wed 13 Dec
Gov 158 | 2017-04-04 | Closed (7/2) | Monthly service manager performance report | Review core standards relating to measuring timescales for CIN meetings | CD CB/AW | 2017-05-31 | 2/2 - CB: Final version to SLT 7/2 - Approved | 27/4 - Work in progress; Core Standards currently state: A Multi Agency Children in Need meeting held within the designated frequency as outlined in supervision, this must be given the same level of importance as Child Protection meetings and core groups. 24/5 - CD & DR have had a discussion and have proposed timescales that need to be circulated to HoS & SM's for consultation then add to core standards document. 29/6: no update 26/7: no update 7/9 - Measure agreed and in place for 0-25 disability service. However this needs to be agreed for localities and incorporated into the core standards. CD to work with Aimee Williams 1/11 - Core standards are being revised by Annie Hunter PSW and will include an appendix that specifically deals with timescales; This is scheduled for consideration at governance board on 7 December 7/12 - to be added to agenda of 10 Jan for formal approval following discussion at SMs meeting on 13 Dec 19/1 - discussed at SLT on 10 Jan; Agreed need to review timescales in light of future Mosaic capability before finalisation and publication
Gov 226 | 2017-09-07 | Closed (2/5/18) | Private fostering protocol | Update and run the revised private fostering protocol through legal services | PB / NH | 2017-10-05 | 27/4 - 27/4 - Protocol has been sent to legal , in relation to the particular query about Cin and payments legal confirm that the answer must be that where a child is privately fostered, and the LA assess that child to be a child in need, then they can provide services which may include providing accommodation and giving assistance in kind or cash (I am quoting from S17(6); ie, the position is the same as with any other child in need. This is reflected in the policy where it outlines financial payments may be considered. | 29/11 - no update received 7/12 - need to follow up with legal to finalise the protocol 8/2 - Private fostering protocol with legal for comments; need to clarify timescale for advice etc; being used as it's a Tri.x protocol
Gov 235 | 2017-10-05 | Closed (13/3) | Workforce profile | Consider way of appointing OTs - e.g. can we look at a model where the NHS is the employer and secondment into the LA? | NL | 2017-10-30 | 2/2 - NL: in January we managed to recruit a permanent OT who is relocating from London and will hopefully start in March 18. The new Senior OT also started in January and is settling in. We have also had a lot of interest in the FTC OTA post which is currently advertised. The one current permanent OT has a Hay6/7 linked grade interview set up for Feb 18. | 29/11 - The NHS as the employer and secondment into the LA would not be our chosen model – NHS terms are different and complex for a manager working in the council to manage alongside council terms (i.e. NHS has a longer working week, longer pay bands, therefore potentially higher salary if person long serving, more annual leave etc.) Preference is to publicise the offer for career progression from Hay 7 to 6 (or direct appointment to Advanced Hay 6 level if essential criteria demonstrated at outset) within 0-25, as agreed at the outset this would also apply to OTs (in 0-25 only) when this process was introduced within ICS. If market factors need to be considered in order to attract applicants once this has been publicised, please discuss with HR Business Partner. 7/12 - OT waiting list is 12 months. Need to do something different. Agreed to try the preferred option initially and review within 3-4 months.
Gov 240 | 2017-11-09 | Closed (10/1) | Missing children and child exploitation report (Q2) | Provide an update to governance board in Dec on the discussion about high risk young people | SM | 2017-12-07 | 10/1 - discussion at 10/1 meeting; please refer to notes | 7/12 - not covered at 7/12 meeting
Gov 247 | 2017-12-07 | Closed (4/4) | Summary of Oct perf analysis | Complete a dip sample of strats to section 47 / ICPC / plan | NL, CD, PB, NH | 2017-12-31 | 28/3 - CD - audit completed, no concerns raised | 2/2 - NL: completed in Dec 17 CD, PB - to confirm position NH - audit completed - currently being written up
Gov 248 | 2017-12-07 | closed (21/2) | Summary of Oct perf analysis | Focus on improving single assessment timescales | NL, CD, PB, NH | 2017-12-31 |  | 2/2 - NL: SM/TM have discussed in 0-25. SA timescales in 0-25 fluctuate month on month but are generally an improving picture. CD, PB, NH - improved position in Jan dataset
Gov 249 | 2017-12-07 | Closed (7/2) | Summary of Oct perf analysis | Analyse November ICPCs to report how many out of timescales were from localities, ART, 0-25 disability and LAC | CB/TW | 2017-12-31 | 2/2 - CB: This is contained in the Q3 report
Gov 250 | 2017-12-07 | Closed (7/2) | QA and Audit | Review "assessments are timely, comprehensive, analytical and of high quality" cf "risk is identified, responded to and reduced in a timely way" to identify why the results are so different. | AH | 2017-12-31 | 2/2 - CB: New style audit report to SLT 21/2
Gov 252 | 2017-12-07 | Closed (7/3) | QA and Audit | Follow up on TMs who didn’t complete an audit in October from the list CB provides | NL, CD, PB, GP, NH | 2017-12-31 | 2/2 - PB?? | 2/2 - NL and GP : 0-25 and preventative Services - n/a NH - followed up each month CD - followed up every month PB -
Gov 253 | 2017-12-07 | closed (21/2) | Deep dive audit summary | Review analysis of data to ensure data conclusions are valid | PM/CB | 2017-12-31 | 2/2 - PM to advise
Gov 254 | 2017-12-07 | Closed (7/2) | corporate parenting exception report | Draft guidance re: single assessments for LAC to be discussed at SMs meeting on Wed 13/12. | NH | 2017-12-13 | 7/2 - confirmed by SLT 7/2; Final version to be sent to Helen Moore for adding to Tri.x and to Service managers for comms with practitioners | 2/2 - drafted; with SM for review prior to SLT formal approval on 7 Feb
Gov 255 | 2017-12-07 | Closed (7/3) | corporate parenting exception report | Discuss permanence planning meetings | CD/NH/SM | 2017-12-15 | 2/3 - Permanency planning protocol approved 7/3 | 2/2 - meeting arranged for 8/2
1 | 2018-01-10 | closed (21/2) | HR workforce data | Ask Comms team to talk to a Response SW to add onto the recruitment website to promote the service | NP | 2018-01-31 | 2/2 - Social Worker name provided by PB to NP and Comms asked to interview ART Social Worker for website on 13/2/18.
2 | 2018-01-10 | closed (21/2) | Mosaic | Continually reiterate the messages regarding the significance of the change for practitioners re: the move to Mosaic and the importance of engaging with Alan's team within the training sessions | NL, CD, PB, GP, NH, CB | ongoing to 12 Mar | 2/2 - CB and NH: ongoing NL: 0-25 completed GP - PS teams engaged in prep and training CD - Ongoing reminders to all staff PB -
3 | 2018-01-10 | Closed (24/1) | High risk young people | Draft initial criteria re: high risk YP and share with SMs | CB, AH | 2018-01-12 | 24/1 - discussed 24/1; refer to action 13
4 | 2018-01-10 | Closed (24/1) | High risk young people | Provide list of high risk CYP (inc YOT) to AH for collation | NL, CD, PB, GP, NH | 2018-01-18 | 24/1 - complete
5 | 2018-01-10 | Closed (24/1) | High risk young people | Collate list of high risk CYP | AH | 2018-01-19 | 24/1 - complete
6 | 2018-01-10 | Closed (24/1) | High risk young people | Set up monthly 30 min slot at SLT to review list of high risk YP | ST | starting from 24/1 | 24/1 - complete; agreed this should be a separate meeting to SLT 9-9.30am on the first Wed SLT meeting in the month.
8 | 2018-01-10 | Closed (7/2) | Core standards | Provide feedback on draft document to AH (especially about timescales – accountability – also need to ensure we can and will be measuring each of the listed outcomes) | NL, CD, PB, GP, NH, CB | 2018-01-15 | 2/2 - CB: Final version to SLT 7/2 NL and GP confirmed feedback provided
9 | 2018-01-10 | Closed (24/1) | Monitoring visit | Update the monitoring visit planning document to include agreed details and reissue | ST | 2018-01-15 | 24/1 - complete
10 | 2018-01-10 | Closed (24/1) | Monitoring visit | Send all requested documents to SM/PM (cc: ST) for QA | NL, CD, PB, GP, NH, CB | 2018-01-17 | 24/1 - complete
11 | 2018-01-10 | Closed (21/3) | AOB | Review measures of success for each IP recommendation to ensure these are giving us the measure of impact required | Recommendation owners | 2018-02-28 | 32/3 - meetings have taken place with ST | 2/2 - meetings booked with ST during Feb/Mar
12 | 2018-01-24 | Closed (7/2) | High risk young people - discussions | Update forward plan to add a 9-9.30 meeting on a monthly basis for SLT to discuss the high risk list of young people. | ST | 29 Feb 18 | 2/2 - complete (circulated with updated action/decision log from meeting)
13 | 2018-01-24 | Closed (7/2) | High risk young people - criteria | Summarise the criteria to be used to determine the list of high risk YP to be monitored by SLT based on the discussion and consider what a potential tracker might look like. | CB | 2018-02-07 | 2/2 - drafted for review by on 7/2
14 | 2018-01-24 | Closed (7/2) | ICS performance dataset | Ask Ed to update performance report to include commentary from the CIN data to the main performance dataset and the commentary about Dec timellness of ICPCs | ST | 2018-01-26 | 2/2 - Complete
18 | 2018-01-24 | closed (21/2) | Deep dive audit summary | Discuss expectations with Team Managers around completing an audit every month and follow up accordingly. | NL, CD, PB, NH | 2018-02-07 | 21/2 - Aimee to now send chasing email to SMs each month | 2/2 - NL, NH: -25 completed 21/2: CD & GP: completed PB, GP -
19 | 2018-01-24 | Closed (7/2) | Deep dive audit summary | Feedback to CB about future format of deep dive report | All | 2018-01-31 | 2/2 - CB: feedback requested at SLT 7/2
22 | 2018-01-24 | Closed (21/3) | CSE and missing | Share attendance at monthly meetings with Heads and Helean Hughes to discuss YP at risk of permanent exclusion. SM to let HH know who will represent ICS. | CD/NH | Ongoing | NH/CD will share attendance. SM has asked HH to invite them to the meetings
23 | 2018-01-24 | Closed (4/4) | CSE and missing | Promote attendance at missing management meetings and reinforce message with TMs to ensure case notes are properly referenced to 'missing management meeting" not risk management meeting. | NL, CD, PB, NH | 2018-02-07 | 28/3 CD - Raised again at TM/SM meeting on 26/3 | 2/2 - NH - complete NL, CD, PB - 2/3 - NL - complete
24 | 2018-01-24 | Closed (7/2) | Potential next sticky issue | Review system/data regarding CP system within their area in preparation for a discussion on 7 Feb | NL, CD, PB, NH, CB | 2018-02-07 | 2/2 -
25 | 2018-01-24 | closed (21/2) | Next meeting | Prepare exception reports for 21 February meeting | PB, CD, GP | 2018-02-21 | 21/2 - exception reports not tabled; assume no red actions / measures from these service area
26 | 2018-02-07 | closed (21/2) | Mosaic rollout | Liaise with Stuart Robinson to arrange a session for him to brief all TMs about Mosaic requirements asap | GP | 2018-02-09 | 21/2 - complete
27 | 2018-02-07 | closed (21/2) | Single assessments for LAC - guidance | Update and provide final copy of the single assessments for LAC guidance to SMs for circulation to TMs and practitioners. Also to send it to Helen Moore for inclusion in next update of Tri.x | NH | 2018-02-13 | 2/3 - updated and sent to SM
28 | 2018-02-07 | closed (21/2) | Monitoring visit | Talk to TMs/practitioners about the visit findings asap - based on presentation circulated by SM. | NL, CD, PB, GP, NH, CB | 2018-02-12 | 21/2 - superceded by comms breifing | 21/2: CD - completed
29 | 2018-02-07 | closed (21/2) | Monitoring visit | Write briefing and circulate to all staff on publication of the letter | SM | 2018-02-23 | 21/2 - draft circulated for comments by cob 21/2
32 | 2018-02-07 | closed (21/2) | Monitoring visit | Meet with NP/Joe Scrase re: recruitment process and concept of peer-coaching. | CD/PB | 2018-02-16 | 21/2 meeting held 13/2 actions agreed
38 | 2018-02-21 | Closed (4/4) | ICS performance data | Review the conversation rates and visiting timescales between North and South data across CIN and report back to next SLT. Also review strategies table at the back of the report | CD | 2018-03-21 | 28/3 - Completed and reported back to SLT on 21/3
39 | 2018-02-21 | Closed (4/4) | Deep dive audit | Service Managers to chase up any audits that haven't been returned (Aimee will now send SMs an email instead of chasing direct) | NL, CD, PB, GP, NH/SW | Ongoing | 28/3 Ongoing - they are reminded every month NH/SW - all Feb audits completed | 9/3 - NL confirmed this was n/a in 0-25
42 | 2018-02-21 | Closed (7/3) | Deep dive audit | Arrange for SMs to meet with Natalie Coles re: Sharepoint version of tracker actions. | AH | 2018-03-07 | 2/3 - scheduled for 7/3 during SLT
43 | 2018-02-21 | Closed (2/5) | QA and Audit | Provide more information on the good practice case from the report to Annie | TW/CP | 2018-02-23 | 28/3 -
45 | 2018-02-21 | Closed (7/3) | QA and Audit - CP plans | Reinforce message about importance of QAR process with CP chairs/IROs and TMs. | TW | 2018-03-07 | 7/3 - CP confirmed this had been done
48 | 2018-02-21 | Closed (7/3) | Ofsted monitoring visit follow up | Arrange for CD visit headings guidance to be added to Tri.x and K drive resources | AH | 2018-03-07 | 2/3 - Sent out to team & actioned
52 | 2018-02-21 | Closed (21/3) | Ofsted monitoring visit follow up | Devise audit template/tool and secure Richard Simpson's time for an audit of permanency cases. | NH/SW, CP | 2018-03-07 | 28/3 - criteria defined and given to Richard Simpson
53 | 2018-02-21 | Closed (21/3) | Ofsted monitoring visit follow up | Identify the case numbers for March deep dive audits where permanency is a factor | NL, CD, PB, GP, NH/SW | 2018-02-23 | 9/3 - NL - complete CD, PN, GP, NH/SW -
54 | 2018-02-21 | Closed (7/3) | AOB | Provide feedback to PB on the following papers to be circulated 22/2 so that these can approved on 7/3 (1) IDVA post, (2) Early Help offer in ART. | All | 2018-03-01 | Feedback received from ST/GP. All to provide feedback to Paul as soon as possible
55 | 2018-02-21 | CLosed (7/3) | AOB | Send report highlighting Managers who will not be Mosaic trained to SMs for follow up. Also to obtain a full list of staff who have not been trained to SMs for follow up. | SM | 2018-02-23
56 | 2018-02-21 | Closed (2/5/18) | AOB | Let staff know there are issues with Survive and that we will issue a briefing note when we know what is happening | NL, CD, PB, GP, NH/SW, CP | 2018-03-07 | 27/4 -Communication was circulated to staff. Survive contracts currently transferring to Julian House including TUPE of existing staff. New communication to be circulated when this has occurred. | 28/3 - NL - complete NH/SW - circulated GP’s e-mail to TMs on 28/3 CD, PN, GP -
58 | 2018-02-21 | Closed (4/4) | AOB | Arrange the sessions with Richard Swan for SMs(12/3) and TMs (26/3) re: group supervisions. | SM | ASAP | 21/3 - 12/3 Session cancelled due to Mosaic rollout; also agreed to cancel 26 March session on 21/3
59 | 2018-02-21 | Closed (4/4) | AOB | Nominate TMs for 26 March training session with Richard Swan | NL, CD, PB, GP, NH/SW, CP | 2018-03-07 | 21/3 - SLT agreed to cancel the 26 March session
60 | 2018-03-07 | Closed (21/3) | HR workforce data | Arrange a meeting to discuss a taskforce approach on recruitment. | NP | 2018-03-16 | 12/3 - meeting took place 13/3
61 | 2018-03-07 | Closed (21/3) | System - Mosaic | Circulate a list of staff, including managers, that are not booked onto Mosaic training - for review by SMs. | AS | 2018-03-07 | 8/3 - Alan circulated the list on 7/3
62 | 2018-03-07 | Closed (21/3) | System - Mosaic | Talk to Catherine Parry about the implications of the Mosaic rollout for IROs/CP Chairs. | AS | 2018-03-08 | 8/3 - Morag briefed Catherine on 7/3
63 | 2018-03-07 | Closed (4/4) | System - Mosaic | Talk to Peter about a proposal to pay staff for additional hours worked to progress the Mosaic implementation | SM/JS | 2018-03-08 | 28/3 - Considered but decision taken not to take it forward
64 | 2018-03-07 | Closed (16/5) | Independent DA Advocate | Discuss possible additional 0.5 FTE funding from LSCB | PM | 2018-03-09 | 9/5 - Agreed by LSCB exec | 12/3 - paper updated; discussed at LSCB on 9/3; proposal going to the board for final agreement
66 | 2018-03-07 | Closed (4/4) | Early help in ART | Discuss and develop a proposal re: an early help pilot in ART for consideration at SLT on 21 March | PB, GP | 2018-03-16 | 28/3 - Discussed and agreed on 21/3 | 13/3 - in progress. Second version circulated for comments
67 | 2018-03-07 | Closed (4/4) | permanency planning protocol | Organise launch of permanency planning protocol to localities and corporate parenting TMs asap | SW/NH, CD | 2018-03-16 | 28/3 - Protocol launched at TM breakfast meeting on 28/3 and meetings have started
68 | 2018-03-21 | Closed (27/4) | SoS implementation | Talk to Claire Brown to set up session for CP Chairs with Jo Radcliffe on the morning of 16 April and to ask for examples of LAs who could provide examples of good CP plans (e.g. Lincolnshire and Norfolk) | CP | 2018-04-04 | 27/4 - SOS session was undertaken, Team continue to review through QA and Team meetings their application to the MOSAIC Plan forms. CP has made contact with Lincolnshire and agreed in principle some support, to be secured for May/June
69 | 2018-03-21 | Closed (27/4) | SoS implementation | Find out what is going on re: SoS implementation and summarise by 4 Apr and send to Claire Brown in order to be clear before SMs meeting with Jo Radcliffe on the afternoon of 16 Apr. Summary to include: • what the team is doing • what the gaps are • what teams would like going forward | NL, CD, PB, GP, NH/SW, CP | 2018-04-04 | Discussed at the meeting on 16 Apr | 28/3 - NH/SW - have update from TMs to be able to share on 4/4
70 | 2018-03-21 | Closed (27/4) | Mosaic rollout | Advise staff that all IT and system issues should be logged on Marval and to use cable not wifi wherever possible. Paul to brief Jackie and Tracey | NL, CD, PB, GP, NH/SW, CP | 2018-03-23 | 28/3 - CD has emailed all staff NH/SW - circulated email to staff on 21/3 NL, PB, GP, CP -
72 | 2018-03-21 | Closed (4/4) | Recruitment | Schedule next meeting of recruitment task force to agree options to be recommended to be added to recruitment/ retention strategy - for consideration on 4 Apr | NP | 2018-03-23 | 28/3 - Meeting took place on 27/3 to consider options and rate them for SLT consideration; SLT considered recommendations on 4/4
74 | 2018-03-21 | Closed (4/4) | Supervision policy and core standards | Circulate updated supervision policy and core standards to Michelle Trigg for onward circulation to Service Managers and Team Managers with deadline for comments/approval of 3 Apr. | CP/MT | 2018-03-27 | 28/3 - Did not happen in this timescale - refer to actions 95-97
75 | 2018-03-21 | Closed (27/4) | Supervision policy and core standards | Develop an implementation timeline for the supervision policy and core standards, inc. the plan for review and audit. | CP/AH | 2018-03-27 | 27/4- completed final documents circulated 22nd April 2018 (CP) | 28/3 - no update provided
76 | 2018-03-21 | Closed (27/4) | Supervision audit | Write up findings of Feb supervision audits and circulate | SM | 2018-03-21 | 27/4 - completed | 28/3 - no update provided
78 | 2018-03-21 | Closed (4/4) | Deep dive audits | Update deep dive report to reflect discussion | CP | 2018-03-22 | 28/3 - recirculated 28/3 and action plan presented to SLT on 4/4
79 | 2018-03-21 | Closed (27/4) | Deep dive audits | Discuss updated deep dive report with TMs for further discussion in teams. | NL, CD, PB, GP, NH/SW, CP | 2018-03-23 | 28/3 - CD - CSE audit findings shared with TM's on 26/3 NH/SW - discussed with TMs 28/3; agreed to provide 1 page summary to assist with sharing with teams by 3/4 NL, PB, GP, CP - Completed and shared by Sonya to all
80 | 2018-03-21 | Closed (27/4) | Deep dive audits | Write staff briefing outlining the findings of the deep dive audits | CP | 2018-03-29 | 27/4 - completed and distributed by Sonya
81 | 2018-03-21 | Closed (4/4) | Deep dive audits | Send brief update on outstanding tracker actions to Sonya before Improvement Board on 27 March. | NL, CD, PB, GP, NH/SW, CP | 2018-03-26 | 28/3 - CD email sent to Sonya. CD to update tracker NH/SW - NH emailed Sonya NL, PB, GP, CP -
86 | 2018-03-21 | Closed (4/4) | ICS performance data | Analyse whether there is a correlation between CL contact timeliness (10.5) and the NEET CLs | NH | 2018-04-18 | 28/3 - see separate short briefing note to SLT- no correlation found (will send on when have final figure from Chris G)
90 | 2018-03-21 | Closed (2/5/18) | ICS performance data | Review the 54 children open on CiN plan for over 12 months in South 2. | CD | 2018-04-04 | 27/4 - This has been completed via CiN panels that have taken place this month across all 4 localities | 28/3- data now gathered re name of children, CD to review with TM on his return from leave
91 | 2018-04-04 | Closed (2/5/18) | Initial feedback from external audits | Act on findings of Enid's audit | SW/CD | 2018-04-18 | 27/4 - Audits from Enid Noctor have been scanned and shared with CSWs and TMs. CSWs and EN have schedule to support SWs to update any actions and TMs will review themes to agree how best to use learning
93 | 2018-04-04 | Closed (2/5/18) | Initial feedback from external audits | Develop a simple template on which results of the SMs dip sample of supervision will be captured | CP | 2018-04-06 | 27/4 - NL and AH completed this
94 | 2018-04-04 | Closed (9/5) | Recruitment | Follow up to implement agreed decisions relating to recruitment recommendations and bring next set of recommendations relating to recruitment to SLT for decision | NP | 2018-05-09 | 27/4 - on forward plan for discussion on 9 May
95 | 2018-04-04 | Closed (27/4) | Supervision policy and core standards | Final versions of documents for onward cascade to be shared with SMs and TMs on 9/4. This will include a one page guide / summary (key expectations) to the set of resources is needed – i.e. the consistent answer to the question “what is our supervision policy?” | CP/AH | 2018-04-09 | 27/4 - completed final documents circulated 22nd April 2018 (CP)
96 | 2018-04-04 | Closed (2/5/18) | Supervision policy and core standards | Brief Nicola and Caryn on what is needed (Siobhan) and Paul/his TMs (Annie) | SW/AH | 2018-04-06 | 27/4 - All briefed and shared with TMs in Corp Parenting & Localities in team meetings (April). Agreed implementation plan with AH

## SI2- out of date (hidden)
ICS SLT
STICKY ISSUE 2 - Critical Thinking, Outcome Focus and Quality of Practice |  |  |  |  | Date initially identified | 2018-02-07
Meeting 1 (7/2) |  |  |  |  | Meeting 2 (21/2/18) | Meeting 3 (21/3/18) | Meeting 4 (4/4/18)
What is the information telling us? | Ref | What are we going to do? | Who is going to do it | Due date | What have we done / what have we found out / what else do we need to do? |  | What improvement have we seen? | Impact
Evidence of critical thinking is not articulated on the file - Is it happening (e.g. informal conversations) and/or is it a case of poor recorded? - Two concrete examples of when this has been observed (CD and SW) informally but probably not then recorded as part of supervision - where does accountability lie? SoS "appreciative enquiry" not included in current Capita templates; will be there in Mosaic | 1 | Define expectations for supervision - set of standards including guidance and ethos - to feed into supervision policy | AH/NL | 2018-02-21 | Drafted - with SM for comments. SM confirmed mostly happy with content but wants to work with Comms about layout to support ease of use. Launch planned at practitioner best practice session on 14 March. Agreed the revised core standards and timescales document will be launched at the same time. Venue to be updated to enable more conducive environment. Each will also be included in Tri.x as part of the next update | Best practice session cancelled due to Mosaic rollout. Now agreed that supervision templates will be finalised/agreed this week (by 23/3) to be put into practice as of 26/3 ahead of the formal launch of the supervision policy after Easter. CATHERINE
Challenges: Are we being realistic and clear about expectations for the TMs? Is the balance between process (e.g. completion of LAC reviews) and critical thinking | 2 | Finalise update of supervision policy | AH | tbc | As per 1 | As above
Do SMs critically challenge TMs during supervision? Do we give answers instead of asking for options? Do we role model the behaviours we want to be? Need to embed the required change in behaviours. | 3 | Role model required behaviours within supervision and discuss expectations | All SMs | 2018-02-21 | Service Managers have had conversations with TMs and agree work is required to facilitate this required step-change in supervision approach. CD has done a lot of work with her TMs on prompts for supervision discussions to support embedding critical thinking. This will form part of the supervision policy. In the meantime, all agreed to use the word template developed by CD with TMs (with agreement to adapt for specific service area if required). | Agreed that copies of SM /TM meeting minutes and/or supervision notes for individual SM/TM 1-1s will be sent to SM. also that SMs will ask TM to share their team meeting notes with SMs. Look to add these into a central shared drive (ST)
Importance of preparing for supervision by SWs | 4 | Set expectations about the importance of SWs preparing for supervision | All SMs | 2018-02-21 | NL confirmed that work is required to support SW think individually re problems - not just come to TM for decisions. AH and NL are meeting Nick Thorne on 28 February to discuss best way to set clear experience and guidance for SWs in preparing for supervision. Guidance will be included in supervision policy.
Supervision template needs updating - we are not helping TMs We've been measuring TM performance through completion of D&A records - this has to shift on move to Mosaic as D&A template not in Mosaic - which will allow more focus on using SoS tools (taking photos etc) | 5 | Finalise new supervision template and expectations | AH | 2018-02-21 | As per 1 | As above
| 6 | Talk to Nick Thorne to get the pack of supervision tools provided by Richard Swan sent to the SMs. Particularly the discrepancy matrix so that this can be used as a tool to facilitate and record informal discussions (focus on asking key questions not providing answers) | SM | 2018-02-21 | AH will check whether Nick T has sent the information. AH to then forward on to SLT and share on the K drive.
Lack of use of genograms/ chronologies within decision making. SMs critical in modelling the need for this | 7 | Look at suitable genogram / chronology tools particularly for use in Mosaic | PB | 2018-02-21 | PB is developing with his TMs and will present at the next SLT. | Jenni Lowe can update on 4/4
Need to shift practice - trajectory planning to achieve outcomes | 8 | Develop guidance re: trajectories | AH/SW | 2018-02-21 | Have examples and continuing to work on this, with good practice examples for inclusion in the supervision policy
| 9 | Define requirements at handover points to ensure consistent approach to trajectory | CD/PB | 2018-02-21 | Not yet started - to form part of action 8 | Meeting had to be postponed due to snow; revised date 16 April
We may not all have the skills/tools to have difficult/challenging conversations with our teams | 10 |  |  |  | SM advised of recent training by Richard Swan re: group supervision with Emma Stephens and Chris Good. Feedback - well received, positive, felt energised. Richard has offered two additional dates. It was agreed that 12 March would be used as a session for SMs at Kingswood if possible, for group supervision session, to include having difficult conversations. 26 March will be used as a session for Team Managers - SMS to provide nominations to SM (1 ART, 2 Localities, 1 Preventative services; ? IRO/CP chairs) asap | Sessions on 12 and 26 March cancelled
Additional discussion at 7/3/18 meeting
SM raised issue of 3 case examples that she had looked at and where practice issues had been identified - but that the "checks and balances" in the system such as IRO/CP Chair oversight, management oversight, had not worked as effectively as it should have to ensure good practice delivery, provide evidence of rationale for decision making and clarity of care planning. Discussion covered issues such as professional accountability, areas such as chronologies/ genograms/ supervision discussions - where can we see impact. What level of discussion is being had with TMs? PSW gave examples of areas of weakness she had seen | 11 | Review of IRO/CP Chair input to each of the 3 specific examples | TW | tbc |  | Catherine will follow up with Tina
| 12 | Mosaic system will enable a view to be taken through dip sampling supervision etc | All SMs | tbc |  | All SMs to do a dip sample of the supervision record on 20 children's files (most recent supervision note on Mosaic for each CYP)
| 13 | Move towards CSWs leading practice challenge / support | CP | tbc |  | Final discussion happening 21/3; Aiming for implementation in w/c 26/3
| 14 | Focus on progressing all above actions | All SMs | tbc |  | Focus of 4/4 meeting will be on: evidencing the progress we have made re: this sticky issue Battle plan for April/May (including response to permanency audits etc)

## Sticky issue 3 (hidden)
ICS SLT
STICKY ISSUE 3 -to be completed by SM 12/3 |  |  |  |  | Date initially identified | 2018-03-07
Meeting 1 |  |  |  |  | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Impact
What is the information telling us? | What are we going to do? | Who is going to do it | Due date | Ref | What have we done / what have we found out / what else do we need to do? | What improvement have we seen?