## Sheet1
Local Transport Priority List competing implementation schemes 2024-25 Last updated 03/01/2025
Local Transport Priority scheme reference	Old Position	Status	Date received	Source of enquiry	Location	Ward	Parish	Area Forum	Outcome	Scheme Type	Budget Provision	Priority
TC11	0	Priority List	Apr-00	Local Residents	Tibberton / Grace Drive / Dyrham Road / Honey Hill Road Area	Woodstock	un-parished	TC	20mph zone with associated traffic calming	Active Travel	£60,000	Recommmended for selection in the 2025-26 programme subject to resources
FV154	0	Priority List	Oct-17	Cycle Group	A432 Old Sodbury to Commonmead Lane	Chipping Sodbury & Cotswold Edge	Sodbury	FV	Share use path between the garage in Old Sodbury to Commonmead Lane. Removing existing grass verge and replacing with tarmac. Relocating VAS	Active Travel	£213,000	Recommmended for selection in the 2025-26 programme subject to resources
TC146	0	Priority List	Nov-24	Resident	A4175 Station Road	Staple Hill & Mangotsfield, New Cheltenham	Staple Hill & Mangotsfield, Kingswood	TC	Zebra Crossing, 20mph and Traffic Calming	Active Travel	£77,000	Recommmended for selection in the 2025-26 programme subject to resources
FV167	0	Priority List	Nov-17	FV31 - Investigation Scheme	Smarts Green Roundabout	Chipping Sodbury & Cotswold Edge	Sodbury	FV	Improve pedestrian crossing facilities move 30mph speed limit and introduce shared use path as dwg T428-315-001B - LINK WITH FV211	Active Travel	£204,000	Recommmended for selection in the 2025-26 programme subject to resources
TC144	0	Priority List	Nov-19	Resident (Jack Lopresti MP)	Peache Rd/ Northcote Rd 20mph and Traffic Calming. Outcome of inv scheme TC119	Frenchay and Downend/Staple Hill and Mangotsfield	Downend & Bromley Heath/Staple Hill & Mangotsfield	TC	20mph and Traffic Calming	Active Travel	£65,000	Recommmended for selection in the 2025-26 programme subject to resources
SB191	0	Priority List	Jan-20	Petition	Old Gloucester Rd (Vantage Park)	Winterbourne	Winterbourne	SB	New footway - outcome of investigation scheme SB133	Active Travel	£150,000	Reserve List
FV217	0	Priority List	Jun-21	Pam Williams	Rodford Way	Dodington	Dodington	FV	Light controlled crossing in Rodford Way at the existing crossing point near the junction of Kelston Close following a request from Road Safety ETP. Pedestrian monitoring supports this measure (Ref 20210505p.xls)	Active Travel	£110,000	Reserve List
KF150	0	Priority List	Jan-18	Local Resident	Woodward Drive	Longwell Green	Oldland	KF	2 x speed tables plus one pair of dropped kerbs	Active Travel	£50,000	Unlikely to be selected in 2025-26
KF131	0	Priority List	Jun-15	SSCG	A420 junction with London Road, Wick	Boyd Valley	Wick and Abson	KF	Traffic island	Network Management	£17,700	Unlikely to be selected in 2025-26
KF90	0	Priority List	Jul-11	Local Member	A420 High Street	Boyd Valley	Wick and Abson	KF	Pedestrian crossing facility	Active Travel	£101,000	Unlikely to be selected in 2025-26
KF161	0	Priority List	Jan-19	Council Leader	Tower Lane, Warmley, near Cadbury Heath Primary	Parkwall & Warmley	Oldland / Siston	KF	Puffin crossing	Active Travel	£100,000	Unlikely to be selected in 2025-26
FV244	0	Priority List	Jan-20	Local Resident and Cllr	Entrances to Yate Academy & St Pauls School, Sundridge Park, Yate	Yate Central	Yate	FV	Pedestrian Improvements at Entrances	Active Travel	£67,750	Unlikely to be selected in 2025-26
FV46	0	Priority List	Nov-10	Local Member & Residents	Nibley Lane to `The Old Parsonage' Westerleigh Village	Frampton Cotterell	Westerleigh	KF	Lack of continuous footway - estimated distance 350m	Active Travel	£200,000	Unlikely to be selected in 2025-26
KF117	0	Priority List	Jul-14	Local Member	Kenilworth Drive, Willsbridge & St Annes Drive, Oldland Common	Longwell Green / Bitton	Oldland / Bitton	KF	Traffic calming to extend / reinforce Cherry Garden Primary 20mph limit	Active Travel	£69,000	Unlikely to be selected in 2025-26
TC39	0	Priority List	Oct-12	Local Resident	Alma Road	Kingswood/Woodstock	un-parished	TC	Junction table and 3 speed tables	Active Travel	£117,000	Unlikely to be selected in 2025-26
KF188	0	Priority List	Sep-22	Oldland Parish Council	Tower Lane / Wraxall Road / Craven Way / Birkdale roundabout	Parkwall & Warmley	Oldland	KF	Pedestrian improvements on Tower Lane approach - footway build out on south side, widened refuge island and new tactile paving	Active Travel	£90,000	Unlikely to be selected in 2025-26
KF195	0	Priority List	Oct-23	Outcome of investigation scheme KF183	A431 Bath Road and Ellacombe Road	Longwell Green	Hanham Abbotts/Oldland	KF	New Zebra Crossing and wr on Bath Rd, upgrade exisitng crossing on Bath Rd, 20mph and raised table o/s school on Ellacombe Rd	Active Travel	£125,000	Unlikely to be selected in 2025-26
KF101	0	Priority List	Apr-13	Local Resident & MP	B4465 Shortwood Road, Pucklechurch	Boyd Valley	Pucklechurch	KF	Speed table north of Homefield Rd junction & speed table outside Post Office	Active Travel	£93,500	Unlikely to be selected in 2025-26
TC134	0	Priority List	Apr-22	Outcome of investigation scheme TC15	Northcote Road	Staple Hill & Mangotsfield	Staple Hill & Mangotsfield	TC	Zebra crossing at existing ped island near Royal Rd junction and move ex. Bus stop. Outcome of investigation TC15, Dwg T303-1478-001 refers	Active Travel	£165,000	Unlikely to be selected in 2025-26
FV71	0	Priority List	Sep-12	Local MP/Resident	B4058 Iron Acton multi-user path	Frampton Cotterell	Frampton Cotterell/Iron Acton	FV	Phase 2 multi user Path between (opp) Hoovers Lane and Cog Mill adjacent to B4058	Active Travel	£273,000	Unlikely to be selected in 2025-26
SB99	0	Priority List	Jul-13	Local Member	Southmead Road - just north of junction with Charborough Road	Filton	Filton	SB	Puffin crossing	Active Travel	£125,000	Unlikely to be selected in 2025-26
TC138	0	Priority List	Jun-22	Outcome of investigation scheme TC128	Westerleigh Road	Frenchay & Downend/Staple Hill & Mangotsfield	Downend & Bromley Heath	TC	Zebra crossing on raised table near Downend School and road closure at Westerleigh Close/Stockwell Close junction. Outcome of investigation TC128, dwg T304-711-002 refers	Active Travel	£149,000	Unlikely to be selected in 2025-26
FV228	0	Priority List	May-22	Westerleigh Parish Council	Roundways/Henfield Rd, Coalpit Heath	Frampton Cotterell	Westerleigh	FV	Waiting restrictions (double yellow lines) along the residential side of Roundways / Henfield Rd (opposite Manor School field), from the junction with Badminton Rd to the junction with Henfield Rd EXTENDING AROUND the junction corner of Roundways and Henfield Road (opposite the entrance to the Manor Hall).	Network Management	£12,500	Unlikely to be selected in 2025-26
FV100	0	Priority List	Oct-13	Local Members	Church Road, Frampton Cotterell	Frampton Cotterell	Frampton Cotterell	FV	Following an investigation scheme in 2013/14 introduce Traffic Management Phase B Provide 4 x Raised Tables in Church Road including improved drainage	Active Travel	£80,000	Unlikely to be selected in 2025-26
KF185	0	Priority List	May-22	Local member - Cllr Steve Reade	A420, Wick High Street - junction with Golden Valley Road	Boyd Valley	Wick and Abson	KF	Continuous footway across junction to discourage unwanted vehicular access to Golden Valley Nature Reserve - see draft drawing T435-116-13	Network Management	£40,000	Unlikely to be selected in 2025-26
SB70	0	Priority List	Feb-13	Local Member	Woodlands Lane signal crossing adjacent to Woodlands Park	Bradley Stoke North	Bradley Stoke	SB	Raise existing signal controlled crossing onto speed table to reduce localised speed.	Active Travel	£55,000	Unlikely to be selected in 2025-26
FV245	0	Priority List	Jun-20	Resident	Various roads in Frampton Cotterell	Frampton Cotterell	Frampton Cotterell	FV	20mph zone & Traffic calming	Active Travel	£119,300	Unlikely to be selected in 2025-26
FV219	0	Priority List	Jul-21	Resident of Old Sodbury	A432 Badminton Road near junction with Catchpot Lane	Sodbury & Cotswold Edge	Sodbury	FV	Following Investigation FV133 - to provide footway from the junction of Catchpot Lane to link up with existing footway adjacent to A432. This scheme is expensive to build and will remain on LTPL if there are grants/bids/S106 money available.	Active Travel	£176,500	Unlikely to be selected in 2025-26
FV145	0	Priority List	Jan-16	Local Councillor	Greenways Rd, Wellington Rd and Halifax Rd	Yate North	Yate	FV	Provision of improved bus stops - shelters in Greenways Road, Wellington Road (north) and Halifax Rd	Public Transport	£86,050	Unlikely to be selected in 2025-26
SV110	0	Priority List	Jul-19	Councillor	A403	Pilning & Severn Beach	Pilning & Severn Beach	SV	Shared use path (south side) - approx. 300m	Active Travel	£300,000	Unlikely to be selected in 2025-26
FV218	0	Priority List	Jul-21	Horton PC	Horton Road	Sodbury & Cotswold Edge	Horton	FV	Following investigation scheme FV17,consultation and a Designation Order is required for Horton Quiet Lanes . See plan No. T417-037-12.	Active Travel	£12,300	Unlikely to be selected in 2025-26
FV233	0	Priority List	to be dated as soon as report is finalised	Outcome of investigation scheme FV201	Randolph Ave	Yate North	Yate	FV	Randolph Ave near the Broad Lane and Churchill Gardens.Install parallel crossing on raised table. Tighten exit radius from roundabout. Tighten entrance and remove island in Churchill Gardens	Active Travel	£288,000	Unlikely to be selected in 2025-26
SV101	NM14/2020	Priority List	May-17	Olveston Parish Council	Washingpool Hill Road, Upper Tockington Road and Lower Tockington Road, Tockington	Severn Vale	Olveston	SV	Area wide parking review	Network Management	£30,000	Unlikely to be selected in 2025-26
SB13	0	Priority List	Mar-02	Area Forum	A4174/Filton Ave, King George VI junction	Filton	Filton	SB	Introduce pedestrian facilities to existing signals - Investigation complete	Active Travel	£530,000	Unlikely to be selected in 2025-26
FV180	0	Priority List	Oct-18	outcome of investigation scheme FV161	Yate Town Centre Area Cycle Routes	Yate Central	Yate	FV	new off-road cycle routes around and through the town centre to connect existing routes and linking to new crossing facilities	Active Travel	£443,500	Unlikely to be selected in 2025-26
FV171	0	Priority List	Nov-17	Outcome of investigation scheme FV136/Local Councillor	Westerleigh Road B4465	Frampton Cotterell/Emersons Green	Westerleigh/Emersons Green	FV	Feasability Study for Cycle Path from Henfield Crossroad to Science Park, Westerleigh on both approaches to new motorway junction. Outcome of investigation scheme FV136	Active Travel	£610,000	Unlikely to be selected in 2025-26
SB179	0	Priority List	Jan-19	0	A4174 / UWE North Entrance	Filton	Filton	SB	Pedestrian / cycle signal crossing upgrade inc controlled crossing on side road	Active Travel	£312,500	Unlikely to be selected in 2025-26
KF136	0	Priority List	Dec-15	Parish Council	Feltham Road	Boyd Valley	Pucklechurch	KF	40mph speed limit extension to Little Nannies Café, BS16 9SJ	Network Management	£20,000	Unlikely to be selected in 2025-26
FV249	0	Priority List	Oct-13	Local Members	B4059 Iron Acton	Frampton Cotterell	Iron Acton	FV	Shared use path adjacent to B4059 between Dyers Lane and B4058 Wotton Road	Active Travel	£501,095	Unlikely to be selected in 2025-26
KF62	0	Priority List	Oct-12	Local Resident	Freezing Hill Lane	Boyd Valley	Cold Ashton	KF	Weight limit / HGV restrictions except for access	Parking & Weight Limit schemes	£33,000	Unlikely to be selected in 2025-26
KF176	0	Priority List	Aug-21	Local member	Conham Hill	Hanham	Hanham	KF	Waiting restrictions from Bristol boundary up the hill to just west of the junction with Lime Road	Parking & Weight Limit schemes	£19,000	Unlikely to be selected in 2025-26
SB40	0	Priority List	Aug-07	Local Member	Braydon Avenue	Stoke Gifford	Stoke Gifford	SB	Removal of subway	Active Travel	£500,000	Unlikely to be selected in 2025-26
KF57	0	Priority List	Jun-16	Local Resident (Petition)	Holmwood, Hanham	Hanham	Hanham	KF	Residents parking	Parking & Weight Limit schemes	£39,000	Unlikely to be selected in 2025-26
SB108	0	Priority List	Sep-13	Local Resident	Pye Corner/Moorend Rd	Winterbourne	Winterbourne	SB	One-way on narrow roads	Network Management	£47,000	Unlikely to be selected in 2025-26
SB172	0	Priority List	Jul-18	Residents	The Sidings / Pilkington Close	Filton	Filton	SB	Area wide waiting restriction review	Parking & Weight Limit schemes	£39,000	Unlikely to be selected in 2025-26
SB169	0	Priority List	Jan-18	Local Businesses	Bradley Stoke	Bradley Stoke North and Bradley Stoke South	Bradley Stoke	SB	Focussed waiting restriction scheme focussing on Ashridge Insdustrial Estate - dwg T439-162-001	Parking & Weight Limit schemes	£40,000	Unlikely to be selected in 2025-26
KF159	0	Priority List	Jan-19	Parish Council	Marshfield Parish	Boyd Valley	Marshfield	KF	Area wide waiting restriction review	Parking & Weight Limit schemes	£50,000	Unlikely to be selected in 2025-26
TC105	0	Priority List	Nov-16	Residents Petition	Midland Rd, Hayward Rd, Howard Rd & North View	Staple Hill & Mangotsfield	Staple Hill & Mangotsfield	TC	RPS in Midland Rd, Hayward Rd, Howard Rd & North View (also review restrictions outside WDM)	Parking & Weight Limit schemes	£47,000	Unlikely to be selected in 2025-26
KF61	0	Priority List	Nov-12	Head Teacher and School Travel Plan	Bristol to Bath Railway Path	Bitton	Bitton	KF	Ramp connecting path to Redfield Edge Primary	Active Travel	£860,000	Unlikely to be selected in 2025-26
FV29	0	Priority List	Jun-08	MP & Local Resident	St John's Way	Chipping Sodbury & Cotswold Edge	Sodbury	FV	Footway between playground and Wickwar Road 85m - drainage issues due to ditch at the rear of the grassed verge which will need lane drainage consent	Active Travel	£50,000	Unlikely to be selected in 2025-26
FV199	0	Priority List	Jan-20	Sodbury Town Council	Horse St/Kingrove Cres/Woodmans Close/Smarts Green/Woodmans Close/Broad Street	Chipping Sodbury & Cotswold Edge	Chipping Sodbury	FV	Horse street area waiting restriction scheme in Chipping Sodbury in Horse St, Kingrove Cres, Woodmans Cl, Smarts Green and changing Taxi operations times in Broad Street Order No. X0905 ECS580160	Parking & Weight Limit schemes	£63,500	Unlikely to be selected in 2025-26
SV102	0	Priority List	Feb-18	Rob Wiltsher	Thornbury Ward	Thornbury	Thornbury	SV	Area-wide Parking Review inc Castle St to expand waiting time opp Stokefield Close	Parking & Weight Limit schemes	£72,000	Unlikely to be selected in 2025-26
SB90	0	Priority List	May-13	Local Member and Local Resident	Northville Road, Filton	Filton	Filton	SB	Review traffic calming	Network Management	£100,000	Unlikely to be selected in 2025-26
SB17	0	Priority List	Oct-06	Airbus	A38 Combination Ground entrance	Filton	Filton	SB	Provide slip road for 'u' turns	Network Management	£132,000	Unlikely to be selected in 2025-26
FV178	0	Priority List	Oct-18	outcome of investigation scheme FV159	Yate Town Centre	Yate Central	Yate	FV	VMS for Town Centre Parking	Network Management	£605,000	Unlikely to be selected in 2025-26
TC114	0	Priority List	Sep-18	Residents & Cllrs	Kingswood Ward	Kingswood	un-parished	TC	Kingswood Ward waiting restriction review	Parking & Weight Limit schemes	£98,000	Unlikely to be selected in 2025-26
TC115	0	Priority List	Sep-18	Residents & Cllrs	Woodstock Ward Phase 3	Woodstock	un-parished	TC	Area Wide waiting restriction review Phase 3	Parking & Weight Limit schemes	£98,000	Unlikely to be selected in 2025-26
SV61	0	Priority List	Jan-13	Local Member	The Village, Aust (St. John's Church)	Severn Vale	Aust	SV	New kerbing alongside church to protect peds and prevent cars destroying verge	Smarter Choices	£169,000	Unlikely to be selected in 2025-26